## Sheet1
# | Action items | Action Description | Assigned To | Status | Start Date | ETA (days) | Comments
1 | NLP integration and changes(Stanford NLP) | figure out how to integrate Stanford NLP to Program AB | BharatiRaja - BOFA | Not Started | 2016-11-17 | 5
2 | Chat UI/Program AB - Use Case 1 | Use Case 1 - Account Balances Chat UI uses BootStrap UI and Jquery to call the Program AB Spring Rest Services Use case should handle complete interaction starting from salutation state (HI) to exit state (Bye). Spring Boot application should call the external OLB specific rest services to get account details etc. Use Responders where ever necessary for simulating external calls. | Shashi/Sujith - BOFA | In progress | 2016-11-17 | 3
3 | Chat UI/Program AB - Use Case 2 | Use Case 2 - Account Closure Follow same approach for this use case also. Use case should handle complete interaction starting from salutation state (HI), calling external services to get transactions and exit state (Bye). Use Responders where ever necessary for simulating external calls. | Saum - BOFA | Not Started | 2016-11-17 | 3
4 | Chat UI/Program AB - Use Case 3 | Use case 3 - Transactions For Eg: How much have I sept on Restaurants Yesterday? Use case should handle complete interaction starting from salutation state (HI), calling external services to get transactions and exit state (Bye). Use Responders where ever necessary for simulating external calls. | Saum -BOFA | Not Started | 2016-11-17 | 3
5 | Program AB Research | 1. How can we make it learn from previous chats? 2. How to persist chat history? 3. How to handle multiple sessions? We need running code samples, not just links | Bharati - Outside BOFA | Not Started | 2016-11-17 | 4
6 | Integration of Program AB research to actual POC code in BOA | Dependency on Task 5 | Shashi/Sujith - BOFA | Not Started | 2016-11-17 | 2